## Sheet1
Background research (4 weeks) |  | Weeks
A | Customer Research/Collect data from survey and interviews | 1 | RI | N/A
B | Current Technologies in market | 1 | RA | N/A
C | Research and evaluate programming languages and frameworks | 2 | SD | A,B
D | Develop project plan and timeline | 2 | PM,SE | A,B
E | Identify potential scource of funding | 1 | RI,RA | D
Design (10 weeks)
Software design
F | Develop software to receive audio and visual data | 3 | SD,HD | E
G | Develop algorithms to identify and clasify objects in the camera feed | 4 | SD, SE, RA | F
H | Design the output audio | 1 | SD, RI | G
I | Distance detection | 1 | SD, SE | H
J | Bluetooth | 1 | SD | I
Hardware
K | Select components that alines with user requirements (speakers, cameras, processors) | 1 | HD | E
L | Design the 3D model | 2 | HD, SE, RI | K
M | Design the PCB board | 3 | HD | L
N | Send the PCB deisgn to manufacture companies and wait for return | 1 | N/A | M
O | Buy the parts from website | 1 | N/A | K
Development (4 weeks)
P | 3D print the cases | 0.5 | HD | L
Q | Assemble the parts/ prototype | 0.5 | HD,SD,SE,PM | M,K
R | Integrate HW and SF | 2 | HD,SD,SE,PM | Q
Testing (4 weeks)
S | Test the prototype for functionality and relability | 2 | HD,SD,SE,PM | R
T | reliability and safety testing | 1 | SE | S
U | Document the testing result and provide feedback to design team for modification | 1 | HD,SD,SE,PM | T
Documentation (2 weeks)
V | Compile the results and reflection in a prototype report. | 2 | PM,RI,RA | U