## Scoring criteria
Use this sheet to record your scoring system. Decide on how you will rate frequency and then add descriptions against the different scores. Do the same for the consequence scores (you may have different types of consequence (cost, schedule, financial etc.) that require you to fill in more than one column.
Team Number
Example chosen:
Frequency ratings (how often is this likely to happen?) |  |  | Consequence ratings
|  |  | Type of Risk = |  |  | Type of Risk = |  |  | Type of Risk =
Category Score | Classification Term | Frequency | Category Score | Classification Term | Description/Examples | Category Score | Classification Term | Description/Examples | Category Score | Classification Term | Description/Examples
1 |  |  | 1 |  |  | 1 |  |  | 1
2 |  |  | 2 |  |  | 2 |  |  | 2
3 |  |  | 3 |  |  | 3 |  |  | 3
4 |  |  | 4 |  |  | 4 |  |  | 4
5 |  |  | 5 |  |  | 5 |  |  | 5

## Risk Assessment
Team Name/Number: |  | group 25, audio camera for the blind
Description and scope of Risk Assessment |  | design a audio camera for the blind which can detect the surrounding environment and inform the bilnd to guild them.
Who are the expected users? |  | blind people
|  |  |  | CURRENT Risk Level |  |  |  | FUTURE Risk Level
Date and Initials of reviewer | Type of Risk | Description of Hazardous event (If…) | Description of Consequence (Then…) | Mitigation(s) | Frequency | Consequence | Risk (fxc) | Additional Mitigation(s) | Frequency | Consequence | Residual Risk
| Operational - Lone working | If the hardware and software developer work alone all day long, it may result in excessive stress, even mental problems. | serious mental problems, low work efficiency | health and safty assist them during the working, talking with them to reduce stress and give support. | 2 | 4 | 8 | ALARP | 2 | 5 | 10
| Operational - Manufacturing | If the developer get injured during the manufacturing when cutting material, soldering ........ | the developer's hand may be get cut or burnt which may not only influence the health but also cause delay. | provide the operator with safety operation training. | 3 | 2 | 6
| Opercational - prototype failure (quality) | if the prototype we bulit went into an error(software, sensor or camera failure etc.) the testing applicant may lose connect with the world immediately or influenced by the wrong command. | the testing applicant may be mislead on the street, it may cause a loss in direction, even if cause a disastrous accdient on the street. | design an extra system to detect the error to give the user warning if something went wrong. | 2 | 5 | 10
| Technical - software bug | if the software design met with bugs need to be revised | the schecdule may be delayed, failure to meet the deadline | ask for professionals help to get rid of the problem | 4 | 2 | 8
| Technical - failure in intrgrate hareware and software | if software and hardware fail to integrate after the manufacturing | it means software not fit the hardware, it may lead to redesign the software or hardware, It may cause huge delay of the project | before starting the design, spend more time to decide the detail and the project manager check the consistency of two groups to prevent mistake. | 2 | 4 | 8
| Technical - perfomance of the prototype. | if the sensor or camera not meet the requirement or meet with protocol problem. | the prototype may have poor proformance. For example, it may fail to detect an object far away or respond too slowly. | Investigate the appropreate sensors for the project then order them on the internet. | 2 | 3 | 6
| Project - headcount | only one person for the software or hardware developer, it may lead to a shortage of personnel. | it may delay the completion of the hardware design and too-much load of one person. | Seek for external help. | 3 | 2 | 6
| Project - funding | if the funding provided cannot support the manufacture of PCB board and model or the purchrse of sensor and camera. | it may delay the completion of the hardware design, | Make sure we meet the deadlines. | 2 | 2 | 4

## Risk Matrix
This is an example criticality matrix. You can develop this to suit your needs. The numbers show the multiples, but you might instead show the number of risks you have in each catergory.
Consequence
|  |  | 1 | 2 | 3 | 4 | 5
|  |  | Minimal | Minor | Moderate | Major | Catastrophic
Frequency | 5 | Almost certain | 5 | 10 | 15 | 20 | 25 | 1-5 Negligible risk: Existing control measures are likely appropriate.
| 4 | Likely | 4 | 8 | 12 | 16 | 20
| 3 | Possible | 3 | 6 | 9 | 12 | 15 | 6-10 Tolerable risk: Additional control measures and mitigations required. Written action plan required.
| 2 | Unlikely | 2 | 4 | 6 | 8 | 10
| 1 | Highly unlikely | 1 | 2 | 3 | 4 | 5 | 11-25 Intolerable risk: Activity must halt. Resumption of activity requires approval from the safety board.
Frequency Definitions
| Almost certain |  | Happens every time in work process.-- equivalent to twice in a week.
| Likely |  | Happens every six work days. --equivalent to once in two weeks
| Possible |  | Once a month
| Unlikely |  | 1%of the time. -- equivalent to once in six months
| Highly unlikely |  | 0.1% of the time. Hardly going to happen during the project
Consequence Definitions
| Catastrophic |  | Cancellation of the project and loss of all fundings. Serious damage to members.
| Major |  | One month of project delay. Loss of main fundings. Damage to members.
| Moderate |  | One week of delay. Loss of half fundings. Small injury to members.
| Minor |  | 2-3 days of delay. Loss of minor fundings. No significant injury.
| Insignificant |  | No delay, loss of fundings less than 10 pounds. No injury at all.